Project Charter Plan

DOST STARBOOKS: Whiz Challenge

DOST Science and Technology Information Institute

Gen. Santos Ave., Upper Bicutan,

Taguig City, Metro Manila, 1631, Philippines

APRIL 2026

Project Charter

DOST STARBOOKS: Whiz Challenge

This Charter formally authorizes the DOST STARBOOKS: Whiz Challenge Project to design, develop, and implement an enhanced gamified quiz application for integration into the existing STARBOOKS platform managed by the Department of Science and Technology – Science and Technology Information Institute (DOST-STII).

A comprehensive project plan will be developed and submitted to the Project Sponsor for approval. The project plan will include the scope statement, schedule, cost estimate, and provisions for scope, resource, schedule, communications, quality, risk, procurement, stakeholder management, and project control.

All resources will be coordinated in collaboration with the Project Sponsor, Ms. Marievic V. Narquita, Information Services Section (ISS) Head of DOST-STII.

The purpose of the DOST STARBOOKS: Whiz Challenge Project is to enhance the engagement, accessibility, and educational effectiveness of the existing STARBOOKS quiz application for Grade 1 to 12 students.

This project addresses the need for improved interactive learning tools by overcoming limitations of the current system, such as the lack of multiple game modes, absence of player progress tracking, and limited engagement features. It also responds to the need for offline-capable educational platforms, particularly in areas with limited or no internet connectivity.

The project deliverables include the design and development of an offline-first gamified application featuring four game modes (Whiz Challenge, Memory Match, Puzzle, and Battle), implementation of a rewards and badge system, player statistics tracking, an enhanced admin dashboard, and system integration with existing STARBOOKS kiosks. A user guide and supporting documentation will also be provided.

The objectives of the project are to increase student engagement, improve frequency of application use, and enhance understanding of science and mathematics concepts through interactive gameplay.

High-level risks include potential challenges in ensuring seamless offline functionality, and maintaining system performance across varying kiosk environments.

Success will be determined by the Project Sponsor based on successful deployment, positive user engagement metrics, increased utilization of STARBOOKS kiosks, and successful completion of pilot testing and system rollout without critical issues.

The Project Manager, Kelly Dumbrique, is hereby authorized to lead and manage the project from planning through deployment. The Project Manager is empowered to coordinate with stakeholders, assign tasks, manage schedules, and oversee project execution to ensure timely and successful completion.

The Project Manager is responsible for developing the project plan, monitoring scope, schedule, and performance, facilitating communication between the development team and DOST-STII, and ensuring that all deliverables meet the required standards. The Project Manager also has the authority to resolve issues, manage risks, and implement corrective actions as necessary.

The project plan will be submitted and approved in accordance with the milestone schedule below. The Project Sponsor must approve any schedule changes which may impact milestones. A detailed schedule will be included in the project plan. The high-level milestone schedule is:

- Requirements Gathering and Planning (April - August 2025)

- Meet with client and stakeholders

- Define scope and core features

- Gather system requirements

- Create use case and system diagrams

- Draft project timeline

- Design initial wireframes

- Development Phase 1 (September - October 2025)

- Finalize system architecture

- Set up development environment

- Build registration and login

- Develop homepage and profile

- Develop Whiz Challenge, Memory Match, and Puzzle games

- Implement player leaderboard and stats

- Development Phase 2 (November 2025 - March 2026)

- Develop 1v1 Battle game

- Finalize core player-side modules (games, rewards, leaderboard)

- Begin development of admin dashboard (user and content management, and difficulty settings)

- Start development of analytics and leaderboard

- Conduct periodic internal testing of core functionalities

- Soft Deployment, Testing, and Player-Side Optimization (April - June 2026)

- Conduct soft deployment in controlled environments (LAN/kiosk setup)

- Perform system-wide testing (focus on player-side modules)

- Conduct user acceptance testing with actual users

- Fix bugs and optimize performance (especially for kiosk hardware)

- Finalize UI/UX polish for player-side features

- Final Deployment, System Completion, and Turnover (July - October 2026)

- Complete and finalize admin dashboard functionalities

- Perform final system integration and validation

- Conduct final testing and bug fixing across all modules

- Finalize all project documentation (SRS, deployment and user manuals, project management)

- Package the system for deployment (kiosk-ready setup)

- Execute full system deployment in target environments

- Conduct project turnover to DOST-STII

The DOST STARBOOKS: Whiz Challenge Project does not require direct financial funding. The project is supported through collaboration with DOST-STII, which provides technical guidance, resources, and strategic oversight.

Development will utilize free and open-source tools, ensuring compatibility with existing STARBOOKS kiosk infrastructure. No additional costs are expected for hardware, software licenses, or deployment.

The project emphasizes cost-efficiency while maintaining high standards of quality, security, and performance.

Sponsor Acceptance

Approved by the Project Sponsor:

Date: April 8, 2026

Marievic V. Narquita

### Information Services Section (ISS) Head of DOST-STII