Risk Management Plan

DOST STARBOOKS: Whiz Challenge

DOST Science and Technology Information Institute

Gen. Santos Ave., Upper Bicutan,

Taguig City, Metro Manila, 1631, Philippines

APRIL 2026

Table of Contents

Introduction	3

Top Three Risks	4

Risk Management Approach	4

Risk Identification	5

Risk Qualification and Prioritization	6

Risk Monitoring	6

Risk Mitigation and Avoidance	7

# Introduction

Every project undertaken in an environment of uncertainty carries inherent risk, which is the possibility that something unforeseen will affect the project's ability to deliver on its scope, schedule, cost, or quality commitments. As a ground-up redevelopment of the existing DOST-STII Whiz Challenge application, the project operates across multiple areas of uncertainty: a student development team with constrained capacity, a government client with evolving requirements, a novel offline-first deployment architecture, and a fixed 2026 deadline. The purpose of this Risk Management Plan is to establish the framework within which the project team identifies these risks, assesses their likelihood and potential impact, and develops strategies to mitigate or avoid them before they affect project outcomes.

This project is assessed as a medium risk project with an overall risk score of 40.9 on a scale of 0 to 100. The project risk score is the average of the risk scores of all identified risks, computed by multiplying each risk's probability rating (0–10) by its impact rating (0–10). A risk score below 16 is a low-risk project, a score between 16 and 45 is a medium risk project, and a score above 45 is a high-risk project.

Before risk management could begin, the following foundational project elements were completed and documented:

Work scope, schedule, resources, and cost elements:

- Work Breakdown Structure and WBS Dictionary developed and maintained in OpenProject across all five project phases

- Sprint-based schedule established with two-week sprints, 10 hours per member per week, 80 total team hours per sprint

- Total project budget of PHP 1,810,000 finalized and baselined across five phases in OpenProject

- All four team members identified and assigned to work packages with defined hourly rates (PHP 500/hour)

- EVM performance measurement metrics established (PV, EV, AC, CV, SV, CPI, SPI) with yellow and red thresholds defined

Minimum and maximum baseline thresholds defined:

- Schedule: SPI yellow at 0.9–0.8 or 1.1–1.2; red at below 0.8 or above 1.2

- Cost: CPI yellow at 0.9–0.8 or 1.1–1.2; red at below 0.8 or above 1.2

- Resources: 10 hours per member per week maximum sustainable allocation

Baseline reporting requirements:

- Format: Sprint Status Reports including EVM metrics, cost variance narrative, and risk status updates

- Frequency: End of each two-week sprint, with phase-level consolidated reports at phase boundaries

- Distribution: Project Sponsor (DOST-STII), Faculty Adviser, full project team

Risk Management Roles and Responsibilities:

- The Project Manager chairs all risk assessment discussions during sprint planning and retrospectives

- All four team members participate in risk identification and serve as risk managers for risks within their functional area

- The Faculty Adviser participates in risk review during weekly Tuesday meetings when risk status updates are warranted

- The Project Sponsor is informed of high-scoring risks and participates in decisions requiring budget or scope changes as risk responses

# Top Three Risks

The following three risks carry the highest risk scores and represent the most significant threats to the successful delivery of the STARBOOKS Whiz Challenge project:

Scope Creep from Continuous Client Feature Additions (R01 — Score: 64)

DOST-STII representatives have consistently introduced new feature requests during sprint reviews and documented during Sprint retrospectives as "scope getting bigger and bigger with every meeting the client adds more features." With a probability of 8 and impact of 8, this is the highest-scoring risk in the register. Left unmanaged, uncontrolled scope additions will destabilize the sprint schedule, exhaust team capacity, and threaten the deployment deadline. The Project Manager will mitigate this risk by enforcing the formal Change Request process for all new feature requests. Any item raised by DOST-STII that falls outside the approved WBS baseline must be submitted as a Change Request, impact-assessed within five business days, and approved by the Project Sponsor before any development work begins. The team will clearly communicate feature priorities to DOST-STII at the start of each sprint review to manage expectations.

Docker / Laragon Deployment Failure on DOST Kiosk Hardware (R05 — Score: 54)

The system's final deployment relies on Laragon and Docker containerization running on DOST-STII's existing kiosk hardware via a LAN configuration. If the kiosk hardware specs are rendered incompatible, if network configuration at event venues does not support the required LAN setup, or if container initialization fails under event conditions, the system will be unusable at its intended deployment environment. With a probability of 3 and impact of 5, this risk is particularly dangerous because it manifests at the very end of the project — in the Closing Phase — where recovery time is minimal. The Project Manager will mitigate this risk by scheduling a full end-to-end deployment rehearsal on DOST-STII hardware at least three weeks before the target deployment date. Laragon is maintained as a fallback deployment stack should Docker-based deployment encounter unresolvable issues on the target hardware.

Project Deadline Not Met Due to Accumulated Delays (R10 — Score: 54)

The project has a fixed deployment target of 2026, driven by academic course deadlines and DOST-STII's event calendar. With a probability of 6 and impact of 9, a missed deadline would constitute a critical project failure — leaving DOST-STII without the promised platform and the team without a completed deliverable for academic evaluation. The primary drivers of this risk are scope creep, team burnout, and high code error volume — all of which compound to erode sprint velocity. The Project Manager will mitigate this risk by maintaining a sprint velocity baseline in OpenProject, monitoring cumulative schedule variance at each sprint boundary, and initiating corrective action, including scope reduction or task reallocation, whenever the SPI drops below 0.9.

# Risk Management Approach

The approach taken to manage risks for the STARBOOKS Whiz Challenge is a continuous, sprint-integrated process embedded directly into the team's Agile/Scrum workflow. Rather than treating risk management as a one-time exercise at project initiation, the team incorporates risk identification and status review into every sprint cycle consistent with PMBOK's emphasis on ongoing risk monitoring throughout the project lifecycle.

Risk identification was conducted through three complementary methods: expert interviews with DOST-STII technical staff during the Empathize stage of Design Thinking, structured risk assessment discussions during sprint retrospectives where the team reflected on what went wrong and what could go wrong, and a systematic review of documented issues from Sprints 3 through 5 including the burnout items, code error volume, scope creep incidents, and deployment concerns surfaced in retrospective records. All identified risks were scored using a Probability × Impact matrix on a 1–5 scale for each dimension, yielding individual risk scores from 1 to 25. Risks scoring 13 or above are classified as High and assigned a dedicated Risk Manager from the project team. Risk Managers provide status updates during sprint reviews when their risk's planned exposure window is active. At project closure, the Project Manager will conduct a retrospective analysis of each risk — whether it materialized, how effective the mitigation was, and what improvements should be captured in the lessons learned register for future projects.

# Risk Identification

Risks for the STARBOOKS Whiz Challenge were identified through the following three methods, conducted across the project's initiation and planning phases and updated continuously through sprint retrospectives:

Expert Interview

Two expert interviews were conducted as part of the Design Thinking Stage 1 (Empathize) on April 30, 2025, with Ms. Marievic V. Narquita (STARBOOKS Unit Head) and Mr. McGyver C. Basaya (STARBOOKS Lead Programmer) at DOST-STII. These interviews revealed risks related to hardware compatibility, content provision dependencies, and data privacy compliance requirements under RA 10173. Several of these risks were mitigated at the planning stage by embedding specific requirements into the SRS and system architecture design.

Risk Assessment through Sprint Retrospectives

The project team conducted structured sprint retrospectives using the Glad / Sad / Mad format in Kollabe at the end of each sprint. These sessions surfaced the following risks through documented participant feedback: scope creep (R01), team burnout (R02), high code error volume (R07), and misaligned expectations between client and panel reviewers. Retrospective findings were transcribed into the Group Log and translated into formal risk register entries by the Project Manager.

Historical Review of Similar Projects

The project team reviewed the documented challenges of similar student-developed government-client projects within the SoCIT program, as referenced during weekly adviser meetings with the project adviser. This review informed risks related to schedule pressure (R10), client availability constraints (R15), and real-time technical feature complexity (R03); risks that commonly recur in comparable project contexts.

# Risk Qualification and Prioritization

All identified risks were qualified using a Probability × Impact scoring matrix on a 1–5 scale for each dimension. Probability reflects the likelihood of the risk occurring within the project's timeframe. Impact reflects the severity of its effect on project objectives — scope, schedule, cost, or quality — if it does occur. The resulting risk score (1–25) determines the risk's priority level and the intensity of monitoring and response required.

| Score Range | Priority Level |
| --- | --- |
| 0-15 | Low — Monitor passively; no dedicated mitigation plan required |
| 16-45 | Medium — Active monitoring; mitigation plan defined and documented in Risk Register |
| 46-100 | High — Dedicated Risk Manager assigned; mitigation actions added to sprint backlog |

The probability-impact assessment was conducted collectively during sprint planning and retrospective sessions, with all four team members contributing ratings and the Project Manager facilitating consensus. Once scored, risks were ranked from highest to lowest score to produce the prioritized Risk Register. All seven high-scoring risks (R01, R02, R03, R04, R05, R07, R10) were immediately assigned risk managers, and their mitigation actions incorporated into active sprint planning.

# Risk Monitoring

Risk monitoring for the STARBOOKS Whiz Challenge is a continuous process embedded into the sprint cadence. All seven High-scoring risks have been added to the OpenProject project plan with assigned Risk Managers, ensuring their status is visible alongside all other project work in the same system.

At each sprint review, the Risk Manager for any risk whose planned exposure window falls within the current sprint will provide a brief status update covering three elements: current risk status (active / watch / closed), whether any trigger conditions have been observed, and whether the planned mitigation remains adequate or requires adjustment.

Trigger conditions have been defined for each high-priority risk to give the Project Manager early warning before a risk becomes an active issue:

- Scope Creep: Trigger — any new feature request from DOST-STII that is not present in the approved WBS baseline. Risk Manager: Groupmate 1 (Project Manager/Product Owner).

- Deployment Failure: Trigger — any compatibility error encountered during pre-deployment testing on DOST hardware, or confirmation that Docker Engine is unsupported on kiosk OS version. Risk Manager: Groupmate 2 (Backend Developer/Technical Lead).

- Deadline Miss: Trigger — SPI drops below 0.9 at any sprint boundary, or cumulative sprint velocity falls more than 15% below the baseline for two consecutive sprints. Risk Manager: Groupmate 1 (Project Manager).

All risk status updates are documented in the Sprint Status Report and archived on SharePoint. If a risk transitions from Watch to Active, the Project Manager escalates the response process within 24 hours — notifying the Faculty Adviser and, if the risk threatens scope, schedule, or budget, the Project Sponsor.

# Risk Mitigation and Avoidance

The Project Manager, with the participation of the full project team, has developed a response strategy for each identified risk. Responses follow four standard PMBOK risk response strategies: Avoid (eliminate the risk by changing the plan), Mitigate (reduce the probability or impact), Transfer (shift the risk to a third party), and Accept (acknowledge the risk and monitor without active response).

The risks for this project will be managed within the triple constraint of scope, schedule, and cost. Of these three constraints, cost is the only one with limited flexibility as a last resort. Time (2026 deployment deadline) and scope (the approved WBS baseline agreed with DOST-STII) are firm constraints. In extreme circumstances, additional budgets may be requested from DOST-STII to bring in supplemental resources or extend the working hours of team members, but only after all other mitigation strategies have been exhausted.

Risk Register

The link to the Risk Register attached below is the complete log of all 15 identified risks for the STARBOOKS Whiz Challenge project. It captures each risk category, probability, impact, risk score, ranking, risk response strategy, trigger condition, and assigned Risk Manager. The register was developed through the initial project risk assessment process and will be updated throughout the project lifecycle as new risks are identified or existing risk statuses change.

Risk Register link

Sponsor Acceptance

Approved by the Project Sponsor:

Date: May 22, 2026

Marievic V. Narquita

Information Services Section (ISS) Head of DOST-STII