## Sheet1
Project Risk Register DOST: STARBOOKS Whiz Challenge
Risk Identification |  |  | Qualitative Rating |  |  |  | Risk Response
ID | Risk | Risk Category | Probability | Impact | Risk Score | Risk Ranking | Risk Response | Trigger | Risk Owner
R01 | Scope creep from continuous DOST-STII feature additions during sprint reviews | Scope | 8 | 8 | 64 | 1 | Avoid/Mitigate — Enforce the formal Change Request process for all out-of-baseline feature requests; communicate feature priorities at sprint review opening; document all new requests in OpenProject before any evaluation begins | Any new feature request from DOST-STII not present in the approved WBS baseline | Kelly Dumbrique (Project Manager / Product Owner)
R05 | Docker and LAN deployment failure on DOST kiosk hardware | Technical | 6 | 9 | 54 | 2 | Mitigate — Schedule full end-to-end deployment rehearsal on DOST hardware at least three weeks before deployment date; maintain Laragon as a tested fallback stack; document both deployment procedures for DOST-STII staff | Any compatibility error or Docker Engine failure observed during pre-deployment rehearsal on kiosk hardware | Arcielle Marie Gercan (Lead Developer)
R10 | 2026 deployment deadline not met due to accumulated schedule delays | Schedule | 6 | 9 | 54 | 3 | Mitigate — Monitor SPI at every sprint boundary; activate corrective action if SPI drops below 0.9; scope reduction of lower-priority admin features is the primary schedule recovery lever | SPI drops below 0.9 at any sprint boundary, or cumulative sprint velocity falls more than 15% below baseline for two consecutive sprints | Kelly Dumbrique (Project Manager / Product Owner)
R02 | Team burnout from concurrent academic workload and client demands | Resource | 8 | 6 | 48 | 4 | Mitigate — Enforce the 10-hour/week allocation limit; redistribute tasks if one member is overloaded; escalate to Faculty Adviser if workload becomes unsustainable | A team member logs more than 15 hours in a single week or raises fatigue concerns during the daily standup | Kelly Dumbrique (Project Manager / Product Owner)
R03 | WebSocket real-time synchronization failure in Whiz Battle mode | Technical | 6 | 8 | 48 | 5 | Mitigate — Conduct dedicated WebSocket integration testing on LAN hardware; implement graceful error handling and reconnection logic; maintain a simplified polling-based fallback if WebSocket is unavailable | WebSocket connection drops or questions appear out of sync between two players during Whiz Battle testing | Arcielle Marie Gercan (Lead Developer)
R04 | Delayed or insufficient provision of quiz content by DOST-STII | External | 6 | 8 | 48 | 6 | Mitigate — Request initial content batch at least four weeks before the content integration sprint; use placeholder content for development; escalate to Project Sponsor if content is not delivered by the agreed milestone | Content not received by the agreed handoff date or delivered in an unusable or incomplete format | Kelly Dumbrique (Project Manager / Product Owner)
R07 | Sprint velocity degradation from high volume of code errors | Quality | 8 | 6 | 48 | 7 | Mitigate — Implement mandatory code review before merging to the main branch; allocate dedicated bug-fix buffer time in each sprint plan; enforce GitHub branch protection rules | More than three unresolved bugs reported in a single sprint, or Sprint Status Report flags SPI below 0.9 | Shandrae Lois Quianzon (Developer / QA Tester)
R06 | MongoDB data loss or corruption during DOST events | Technical | 4 | 9 | 36 | 8 | Mitigate — Implement and document daily database backup procedures for DOST-STII staff; include backup and restore instructions in the user manual; perform mandatory pre-event backup as a checklist item | Database error, unexpected server shutdown, or hardware failure during an active event session | Arcielle Marie Gercan (Lead Developer)
R08 | Key team member unavailability mid-sprint due to academic obligations | Resource | 6 | 6 | 36 | 9 | Accept/Mitigate — Cross-train team members on each other's primary work packages; document all active tasks in OpenProject so any member can continue another's work; communicate absences at least 48 hours in advance | A team member announces unavailability with less than 48 hours notice during an active sprint | Kelly Dumbrique (Project Manager / Product Owner)
R09 | DOST-STII kiosk hardware specifications below system minimum requirements | External | 4 | 9 | 36 | 10 | Mitigate — Validate hardware specifications against SRS minimum requirements (Intel Core i3, 4GB RAM, 50GB storage) during pre-deployment rehearsal; optimize application for lower-spec hardware if needed | Hardware spec sheet from DOST-STII confirms processor, RAM, or storage below SRS-defined minimum thresholds | Arcielle Marie Gercan (Lead Developer)
R11 | Flutter web application performance degradation under 15 concurrent users | Technical | 6 | 6 | 36 | 11 | Mitigate — Conduct load testing simulating 15 concurrent users before deployment; optimize API queries and implement connection pooling; validate against performance requirements PR-011 and PR-012 in the SRS | Response time exceeds SRS thresholds during internal load testing with simulated concurrent sessions | Arcielle Marie Gercan (Lead Developer)
R12 | Unclear or continuously changing requirements from DOST-STII | Scope | 6 | 6 | 36 | 12 | Mitigate — Document all requirements in the SRS and obtain DOST-STII review sign-off before development begins; treat all post-baseline requirement changes as formal change requests; revisit scope at each sprint review | DOST-STII requests modification to a feature already developed and accepted in a prior sprint review | Kelly Dumbrique (Project Manager / Product Owner)
R13 | Data privacy non-compliance with Philippine Data Privacy Act (RA 10173) | External | 4 | 9 | 36 | 13 | Avoid — Embed all RA 10173 compliance requirements directly into the SRS and system design; implement password hashing, minimal data collection, privacy notice during registration, and role-based access control as non-negotiable system requirements | Security review identifies personal data stored without cryptographic hashing, consent acknowledgment, or appropriate access controls | Arcielle Marie Gercan (Lead Developer)
R15 | Faculty Adviser or DOST-STII unavailability for scheduled sprint reviews | External | 4 | 5 | 20 | 14 | Accept — Build buffer into the sprint review schedule; confirm meeting availability at least three days in advance; conduct asynchronous feedback collection via email if in-person review must be postponed | Review meeting not confirmed 48 hours before the scheduled date | Kelly Dumbrique (Project Manager / Product Owner)
R14 | Loss of OpenProject data or project tracking system failure | Technical | 2 | 7 | 14 | 15 | Accept — Export OpenProject data regularly to SharePoint as a backup; maintain Sprint Status Reports and WBS documentation independently as offline records | OpenProject becomes inaccessible for more than one full working day | Janice Maxene Salipande (Scrum Master)
Key Terms
Risk: The risk stated in a complete sentence which states the cause of the risk, the risk, and the effect that the risk causes to the project.
Risk Category: Categorization of risks by area of project affected, source of risk or other useful category.
Probability: The likelihood that a risk or opportunity will occur (on a scale from 0 to 10 with 10 being the highest).
Impact: The impact of the risk on the project if the risk occurs (scale from 0 to 10 with 10 being the highest).
Risk Score: Determined by multiplying probability and impact (scale from 0 to 100).
Risk Ranking: A priority list which is determined by the relative ranking of the risks (by their scores) within the project with the number one being the highest risk score.
Risk Response: The action which is to be taken if this risk occurs.
Trigger: Something which indicates that a risk is about to occur or has already occured.
Risk Owner: The person who the project manager assigns to watch for triggers, and manage the risk response if the risk occurs.
This Risk Register Template is brought to you by www.projectmanagementdocs.com