Cost Management Plan

DOST STARBOOKS: Whiz Challenge

DOST Science and Technology Information Institute

Gen. Santos Ave., Upper Bicutan,

Taguig City, Metro Manila, 1631, Philippines

APRIL 2026

Table of Contents

Introduction	3

Cost Management Approach	3

Measuring Project Costs	3

Reporting Format	7

Cost Variance Response Process	7

Cost Change Control Process	8

Project Budget	8

# Introduction

The Cost Management Plan for the STARBOOKS Whiz Challenge project defines how project costs are planned, tracked, and controlled across the three development sprints completed within the term. Instead of a traditional phase-based structure, the project follows a sprint-based Agile approach where each sprint serves as a control period for monitoring cost and performance.

The Project Manager is responsible for overseeing cost tracking and reporting throughout all three sprints, ensuring that actual spending aligns with planned labor effort and deliverables. Cost performance is evaluated at the end of each sprint using Earned Value Management (EVM), allowing the team to measure both cost efficiency and delivery progress based on completed outputs.

During sprint review meetings, the Project Manager presents cost performance results to the team and project stakeholders from DOST-STII. These reports highlight any variances between planned and actual costs, as well as the corresponding completion of deliverables. Any significant deviations are analyzed, and appropriate corrective actions are discussed to ensure continued alignment with project objectives.

The Project Sponsor (DOST-STII) retains final authority over any budget-related adjustments or corrective measures that may affect scope, schedule, or resource allocation. This ensures that all cost-related decisions remain aligned with institutional guidelines and project constraints.

# Cost Management Approach

Costs for the STARBOOKS Whiz Challenge project are managed using a sprint-based cost control structure aligned with the Agile development process. Instead of traditional project phases, each of the three completed sprints serves as a Control Account (CA), where cost performance and deliverables are tracked independently.

Each sprint includes planned labor effort distributed among four team members. Cost estimation is based on a standardized labor rate of PHP 500.00 per hour, with each member allocated 50 hours per sprint. This results in a planned cost of PHP 100,000.00 per sprint.

Cost tracking is primarily focused on labor expenditures, as the project operates under a government-sponsored development environment provided by DOST-STII. As a result, no direct unit or procurement costs were incurred, and all necessary tools, platforms, and infrastructure were provided as institutional support.

The project uses Earned Value Management (EVM) to measure cost and performance at the end of each sprint. Planned Value (PV), Earned Value (EV), and Actual Cost (AC) are recorded based on completed deliverables and logged labor effort per sprint. This allows the team to assess whether work completed aligns with the planned budget and schedule.

Labor costs are tracked per sprint based on actual hours rendered by each team member. Any variation between planned effort and actual output is reflected in the EVM performance indicators (Cost Variance and Cost Performance Index), which are reviewed during sprint evaluation.

A CPI or SPI threshold is used to determine performance status. Values between 0.9 and 1.1 are considered acceptable (green zone), while deviations beyond this range require review and justification. This ensures that cost efficiency and delivery performance remain within acceptable project limits throughout all sprint cycles.

All cost-related tracking and documentation are maintained through the project’s management system, ensuring transparency and traceability of labor effort and deliverables across all sprints.

# Measuring Project Costs

Project costs for the STARBOOKS Whiz Challenge are measured using Earned Value Management (EVM), in accordance with PMBOK guidelines. EVM is applied at the sprint level to evaluate both cost and schedule performance across the three completed development sprints. This allows the Project Manager to assess progress based on actual deliverables completed per sprint rather than overall project completion.

Cost data is based on labor effort recorded per sprint. Each of the four team members is assigned a standard rate of PHP 500.00 per hour, with 50 planned hours per sprint, resulting in a planned cost baseline of PHP 100,000.00 per sprint.

Each sprint functions as an independent measurement period with its own Planned Value (PV), Earned Value (EV), and Actual Cost (AC), which are used to compute cost and schedule performance indicators.

Sprint-Based EVM Baseline

Each sprint uses the following baseline:

- Planned Value (PV) = PHP 100,000.00 per sprint

- Earned Value (EV) = Based on percentage of completed deliverables per sprint

- Actual Cost (AC) = Recorded labor cost per sprint

Sprint EVM Summary

- Sprint 1 (Mar 23 – Apr 3)

  - PV = PHP 100,000.00

  - EV ≈ PHP 90,000.00 (based on 90–95% completion of deliverables)

  - AC = PHP 46,500.00

- Sprint 2 (Apr 13 – Apr 24)

  - PV = PHP 100,000.00

  - EV ≈ PHP 95,000.00 (based on 95–97% completion of deliverables)

  - AC = PHP 32,500.00

- Sprint 3 (Apr 27 – May 8)

  - PV = PHP 100,000.00

  - EV = PHP 100,000.00 (100% completion of deliverables)

  - AC = PHP 13,000.00

Earned Value Metrics per Sprint

1. Schedule Variance (SV)

Schedule Variance measures whether the project is ahead or behind schedule by comparing Earned Value (EV) and Planned Value (PV).

- SV = EV − PV

Interpretation:

- SV = 0 → On schedule

- SV > 0 → Ahead of schedule

- SV < 0 → Behind schedule

2. Cost Variance (CV)

Cost Variance measures budget performance by comparing Earned Value (EV) and Actual Cost (AC).

- CV = EV − AC

Interpretation:

- CV = 0 → On budget

- CV > 0 → Under budget

- CV < 0 → Over budget

3. Schedule Performance Index (SPI)

SPI measures schedule efficiency.

- SPI = EV ÷ PV

Interpretation:

- SPI = 1.0 → On schedule

- SPI > 1.0 → Ahead of schedule

- SPI < 1.0 → Behind schedule

4. Cost Performance Index (CPI)

CPI measures cost efficiency.

- CPI = EV ÷ AC

Interpretation:

- CPI = 1.0 → On budget

- CPI > 1.0 → Under budget

- CPI < 1.0 → Over budget

Sprint Performance Summary

| Sprint | PV | EV | AC | CV | CPI | SPI | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | 100,000 | 90,000 | 46,500 | +43,500 | 1.94 | 0.90 | On schedule / Under budget |
| Sprint 2 | 100,000 | 95,000 | 32,500 | +62,500 | 2.92 | 0.95 | On schedule / Under budget |
| Sprint 3 | 100,000 | 100,000 | 13,000 | +87,000 | 7.69 | 1.00 | Completed / Under budget |

# Reporting Format

Cost reporting is conducted at the end of each sprint through the Sprint Status Report. Each report includes a Cost Management section containing SV, CV, SPI, and CPI for that sprint, along with a comparison of planned versus actual labor costs and a narrative explanation of any variances.

All significant deviations from expected performance are documented and reviewed during sprint evaluation meetings. These reviews ensure that cost efficiency and deliverable completion remain aligned with project objectives throughout all sprint cycles.

# Cost Variance Interpretation

Cost reporting is conducted at the end of each sprint through the Sprint Status Report. Each report includes a Cost Management section containing SV, CV, SPI, and CPI for that sprint, along with a comparison of planned versus actual labor costs and a narrative explanation of any variances.

All significant deviations from expected performance are documented and reviewed during sprint evaluation meetings. These reviews ensure that cost efficiency and deliverable completion remain aligned with project objectives throughout all sprint cycles.

Sponsor Acceptance

Approved by the Project Sponsor:

Date: May 22, 2026

Marievic V. Narquita

Information Services Section (ISS) Head of DOST-STII