Project Status Report For Sprint 06

DOST STARBOOKS: Whiz Challenge

Duration: March 23, 2026 – April 3, 2026

Project Status Summary		Percent Complete:	90-95%

| Area | Status | Remarks |
| --- | --- | --- |
| Scope |  | All tasks aligned with planned UI/UX refinements and system improvements |
| Schedule |  | Sprint tasks were mostly completed on time |
| Risks |  | Minor risks due to ongoing admin-side adjustments and system consistency issues |
| Quality |  | Significant improvements in UI consistency, usability, and responsiveness |

This sprint focused on refining the user interface, improving gameplay layout consistency, and aligning both player-side and admin-side functionalities. Most tasks were completed successfully, particularly across all game modes. Minor delays are present in some admin-side features (e.g., Players and Admins menu adjustments), but these are expected to be resolved in the next sprint. Overall, the project remains on track with no major blockers.

# Work Planned for Last Sprint

- Fix admin profile image functionality

- Improve Players menu (table layout, forms, password handling)

- Implement admin management restrictions (prevent self-delete, ensure at least one admin remains)

- Refine Questions menu (table alignment, CSV import validation, add image support)

- Adjust Difficulty settings (correct color coding)

- Fix and make Analytics dashboard fully dynamic

- Fix and standardize Leaderboard module

- Align UI labels and terminology across admin forms

# Work Completed This Sprint

General UI & System Improvements

- Added DOST-STII logo to splash screen

- Standardized terminology (e.g., “Select Avatar”, “Current Password”) across system

- Implemented session persistence (refresh does not return to splash screen except during games)

- Added Edit Profile access in Settings

Game Mode Enhancements

- Whiz Challenge

  - Improved layout spacing and readability

  - Adjusted timer, question, and answer positioning

  - Implemented responsive question container

  - Standardized difficulty color coding

  - Integrated music control within pause dialog

- Whiz Memory Match & Whiz Puzzle

  - Added centralized music control within pause dialog

  - Fixed missing badge icon in results screen (Puzzle)

  - Standardized difficulty color coding (Puzzle)

- Whiz Battle

  - Removed unnecessary copy-paste icon (kiosk context)

  - Added music control (since no pause menu)

  - Improved layout consistency with Whiz Challenge

  - Added answer selection feedback indicator

  - Improved spacing and readability

Leaderboard Updates

- Redesigned leaderboard structure to match admin data

- Removed per-game rankings; unified into total badges and stars

- Updated sections: Stars, Badges, Memory Match, Puzzle

- Fixed UI alignment issues

Admin Panel Improvements

- Fixed admin profile image update issue

- Updated naming consistency across forms

- Implemented restrictions:

  - Prevent deleting last admin

  - Prevent self-deletion

# Work Planned For Next Sprint

- Enhance badge display system:

  - Replace lock icons with grayscale badge icons for unearned badges (player side and admin “View Badges”)

- Implement Text-to-Speech (TTS) feature for Whiz Challenge:

  - System reads the question before the timer starts

  - TTS is independent from background music (mute only affects music)

  - Not applied to Whiz Battle

- Continue refinement of Questions menu (Admin Panel):

  - Adjust table layout and column alignment

  - Remove unnecessary status column

  - Improve CSV import validation (duplicates, empty cells, incomplete entries)

  - Add image upload support for question and answer choices (if not yet fully completed)

- Implement bulk selection feature:

  - Add select/select-all checkboxes for batch actions in Questions menu

- Continue admin panel polishing and consistency fixes

# Open Issues

| Issue | Status | Action |
| --- | --- | --- |
| Players table layout uneven spacing | In Progress | UI adjustment ongoing |
| Admin self-delete restriction logic | In Progress | Backend validation being implemented |
| Password form consistency (admin side) | In Progress | Aligning with player-side implementation |

# Open Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Remaining admin inconsistencies | Medium | Medium | Prioritize admin module completion next sprint |
| Time constraints for final testing | High | High | Allocate dedicated testing phase in next sprint |
| UI issues on actual kiosk device | Medium | High | Conduct early kiosk-based testing |

# Deliverables and Milestones

| Milestone | Planned | Forecasted | Actual | Status |
| --- | --- | --- | --- | --- |
| UI/UX Standardization | This Sprint | This Sprint | Completed | Completed |
| Game Mode Enhancements | This Sprint | This Sprint | Completed | Completed |
| Admin Panel Fixes | This Sprint | Next Sprint | - | In Progress |

# Open Change Requests

| Change | Status |
| --- | --- |
| Standardize difficulty color coding across all game modes | Completed |
| Modify leaderboard structure (remove per-game rankings) | Completed |
| Adjust UI layout for kiosk usability | Completed |
| Admin restrictions (delete/self-delete rules) | In Progress |

# Key Performance Indicators (KPI's)

Schedule Performance – Project is On Schedule

- Total Tasks Planned: ~45

- Completed Tasks: Majority (over 90%)

- In Progress Tasks: 4–5 remaining admin-related tasks

Schedule Completion Rate

Schedule Completion=Completed TasksTotal Planned Tasks≈90%-95%

Interpretation:
The project is currently on schedule, with most sprint tasks completed within the planned timeframe. A small number of tasks, primarily related to admin panel refinements, are still in progress but are not critical blockers and are expected to be completed in the next sprint.

Cost Performance – Project is Under Budget

- Planned Budget: PHP 100,000.00

- Actual Cost (Spent): PHP 46,500.00

- Remaining Budget: PHP 53,500.00

- Percent Spent: 47%

Cost Variance (CV)

CV=Planned-Actual=100,000-46,500=PHP 53,500

Interpretation:
The project is currently under budget, with a positive cost variance of PHP 53,500. This indicates that expenses are being managed efficiently, and available resources are sufficient for upcoming development phases.

Cost Performance Index (CPI)

CPI=Planned/Actual=100,000/46,500≈2.15

Interpretation:
A CPI greater than 1 indicates strong cost efficiency. A value of 2.15 means that for every peso spent, the project is gaining more value than expected, reflecting effective resource utilization.