Project Status Report For Sprint 07

DOST STARBOOKS: Whiz Challenge

Duration: April 13, 2026 – April 24, 2026

Project Status Summary		Percent Complete:	95-97%

| Area | Status | Remarks |
| --- | --- | --- |
| Scope |  | All planned UI/UX enhancements and admin refinements completed |
| Schedule |  | Sprint completed within planned duration |
| Risks |  | No major risks identified this sprint |
| Quality |  | Significant improvements in usability, accessibility, and system consistency |

This sprint focused on completing remaining UI/UX enhancements and admin-side refinements, particularly improving accessibility, usability, and system interaction consistency. Key features such as badge visualization improvements, text-to-speech integration, and advanced admin question management tools were successfully implemented. The system is now more stable and closer to final production readiness, with no major blockers identified.

# Work Planned for Last Sprint

- Enhance badge display system:

  - Replace lock icons with grayscale badge icons for unearned badges (player side and admin “View Badges”)

- Implement Text-to-Speech (TTS) feature for Whiz Challenge:

  - System reads the question before the timer starts

  - TTS is independent from background music (mute only affects music)

  - Not applied to Whiz Battle

- Continue refinement of Questions menu (Admin Panel):

  - Adjust table layout and column alignment

  - Remove unnecessary status column

  - Improve CSV import validation (duplicates, empty cells, incomplete entries)

  - Add image upload support for question and answer choices (if not yet fully completed)

- Implement bulk selection feature:

  - Add select/select-all checkboxes for batch actions in Questions menu

- Continue admin panel polishing and consistency fixes

# Work Completed This Sprint

- Badge System Enhancement

  - Replaced lock icons with grayscale badge icons for unearned badges

  - Applied changes to both player-side and admin “View Badges” section

- Text-to-Speech (TTS) Feature

  - Implemented question reading before timer starts in Whiz Challenge

  - Ensured TTS operates independently from background music controls

  - Excluded TTS functionality from Whiz Battle (as specified)

- Admin Questions Menu Improvements

  - Improved table layout and column alignment

  - Removed unnecessary status column

  - Enhanced CSV import validation (duplicates, empty cells, incomplete data)

  - Added image upload support for question text and choices

- Bulk Selection Feature

  - Implemented select/select-all checkbox functionality

  - Enabled batch actions for question management

# Work Planned For Next Sprint

- Documentation Phase

  - Business Model Canvas

  - Feasibility Study

  - Risk Management Plan

  - Requirements Management Plan

  - Risk Register

  - Configuration Management Plan

  - Change Management Plan

  - Project Status Reports

  - Transition Out Plan

  - Project Acceptance Document

  - Post Project Review

  - Lessons Learned Document

- System Optimization

  - Player-side optimization and performance tuning

  - Final UI/UX polishing for kiosk deployment readiness

# Open Issues

None identified for this sprint

# Open Risks

No active risks currently identified

(System is in stable phase; remaining risks are low and related only to final documentation and optimization phase)

# Deliverables and Milestones

| Milestone | Planned | Forecasted | Actual | Status |
| --- | --- | --- | --- | --- |
| Badge System Enhancement | This Sprint | This Sprint | Completed | Completed |
| TTS Feature Implementation | This Sprint | This Sprint | Completed | Completed |
| Admin Questions Menu Upgrade | This Sprint | This Sprint | Completed | Completed |
| Bulk Selection Feature | This Sprint | This Sprint | Completed | Completed |

# Open Change Requests

| Change | Status |
| --- | --- |
| Badge grayscale redesign | Completed |
| Text-to-Speech integration | Completed |
| Admin question bulk selection feature | Completed |
| CSV validation improvements | Completed |

# Key Performance Indicators (KPI's)

Schedule Performance – Project is On Schedule

- Total Tasks Planned: ~50+ cumulative system tasks

- Completed Tasks: Majority (>95%)

- In Progress Tasks: Minimal / none critical

Schedule Completion Rate:
≈ 95% – 97%

Interpretation:
The project remains on schedule with all Sprint 07 deliverables completed successfully. The system is now transitioning from feature development to documentation and final optimization phase.

Cost Performance – Project is Under Budget

- Planned Budget: PHP 100,000.00

- Actual Cost (Spent): PHP 32,500.00

- Remaining Budget: PHP 67,500.00

- Percent Spent: 32.5%

Cost Variance (CV):
PHP 67,500.00

Cost Performance Index (CPI):
≈ 3.08

Interpretation:
The project remains significantly under budget, indicating highly efficient resource utilization and minimal operational cost due to the use of free development tools and institutional support from DOST-STII.