Transition Out Plan

DOST STARBOOKS: Whiz Challenge

DOST Science and Technology Information Institute

Gen. Santos Ave., Upper Bicutan,

Taguig City, Metro Manila, 1631, Philippines

APRIL 2026

Table of Contents

1.	Executive Summary	3

2.	Transition Approach	3

3.	Transition Team Organization	4

4.	Workforce Transition	5

5.	Work Execution During Transition	5

6.	Subcontracts	6

7.	Property Transition	6

7.1.	Government Furnished Equipment (GFE)	6

7.2.	Incumbent Owned Equipment	7

7.3.	Intellectual Property	7

7.4.	User Accounts and Passwords	7

8.	Knowledge Transfer	8

9.	Schedule	8

10.	Handover and Acceptance	9

# Executive Summary

This Transition Out Plan formally documents the process for the handover of the STARBOOKS Whiz Challenge system including all source code, documentation, data, and operational knowledge from NEXUS (development team) to the Department of Science and Technology – Science and Technology Information Institute (DOST-STII). It describes the approach, team responsibilities, knowledge transfer activities, property transition, and acceptance process required to complete the project's formal closure.

The STARBOOKS Whiz Challenge is a ground-up redevelopment of the existing DOST-STII Whiz Challenge application, built as a gamified, offline-first educational platform for STEM learning. The system features four interactive game modes (Whiz Challenge, Whiz Memory Match, Whiz Puzzle, and Whiz Battle), a badge and reward system, a player leaderboard, and a fully featured administrative dashboard. It was developed by NEXUS under the guidance of Faculty Adviser Sir Jose Eugenio Quesada and in partnership with DOST-STII, represented by Ms. Marievic V. Narquita (STARBOOKS Unit Head) and Mr. McGyver C. Basaya (STARBOOKS Lead Programmer), from project initiation in April 2025 through the targeted deployment date of October 2026.

Upon completion of all transition activities, full ownership of the STARBOOKS Whiz Challenge system — including all intellectual property, source code, database, documentation, and deployment assets — will transfer to DOST-STII.

# Transition Approach

The overall approach to this transition prioritizes knowledge continuity, documentation completeness, and DOST-STII's operational independence after handover. The goal is to ensure that DOST-STII technical staff can independently deploy, operate, manage, and maintain the STARBOOKS Whiz Challenge system at DOST events without requiring any further involvement from the development team.

The team will maintain its full four-member composition throughout the transition period. No additional staffing is required. All four team members will remain actively available to support knowledge transfer activities, answer technical queries, resolve outstanding issues identified during User Acceptance Testing (UAT), and finalize all documentation deliverables. Active development work will wind down during the transition period, with effort redirected toward documentation, training preparation, deployment rehearsal, and UAT support.

The following assumptions underpin this transition plan:

- DOST-STII will designate a technical point of contact — Mr. McGyver C. Basaya (STARBOOKS Lead Programmer) — to participate in all technical knowledge transfer sessions and receive the deployment package.

- DOST-STII will make the necessary hardware available for the end-to-end deployment rehearsal before the final handover date.

- DOST-STII will provide adequate physical workspace and network access for the team members during on-site knowledge transfer sessions.

- All UAT feedback received during the transition period will be limited to defect corrections and minor adjustments within the approved WBS scope. New feature requests will be formally declined or documented as post-handover enhancement opportunities for DOST-STII.

- The Project Adviser will be available for the final review meeting during the transition period.

# Transition Team Organization

The following table defines all roles and responsibilities for the 30-day transition period. The transition team is composed of members from the development team and DOST-STII, with the Faculty Adviser serving as an independent quality reviewer.

| Organization | Name / Role | Title | Responsibilities |
| --- | --- | --- | --- |
| DOST-STII | Ms. Marievic V. Narquita | Project Sponsor / STARBOOKS Unit Head | Provide formal acceptance of all transition deliverables; sign the project turnover record; ensure DOST-STII internal resources and workspace are available throughout the transition period |
| DOST-STII | Mr. McGyver C. Basaya | STARBOOKS Lead Programmer / Technical Transition Lead | Attend all technical knowledge transfer sessions; receive and validate the deployment package; confirm system operability on DOST kiosk hardware; serve as the primary technical point of contact post-handover |
| DOST-STII | STARBOOKS Unit Staff | End Users | Participate in user acceptance testing; validate player-side and admin-side functionality against operational requirements; provide formal UAT sign-off |
| APC-SoCIT | Kelly Dumbrique | Project Manager / Product Owner / Transition Lead | Coordinate and schedule all transition activities; provide weekly transition progress reports to DOST-STII and Faculty Adviser; ensure all deliverables are complete before handover; obtain all required signatures on closure documents |
| APC-SoCIT | Arcielle Marie Gercan | Lead Developer / Backend Transition Lead | Lead all technical knowledge transfer sessions on system architecture, MongoDB administration, and API structure; deliver and validate the deployment package on DOST hardware |
| APC-SoCIT | Shandrae Lois Quianzon | Frontend Developer | Support knowledge transfer on player-side Flutter application features; assist with UAT defect resolution on game modes and player interface |
| APC-SoCIT | Janice Maxene Salipande | Frontend Developer / Documentation Lead | Finalize and deliver all documentation including SRS, System Design Document, User Manual, Setup and Deployment Instructions, and archived project records; ensure all documents are uploaded to SharePoint |
| APC-SoCIT | Sir Jose Eugenio Quesada | Faculty Adviser | Attend the final project review meeting; verify completeness of academic deliverables; provide independent endorsement of project closure |

# Workforce Transition

All team members will remain engaged and available for the transition period. No team member will disengage from the project until the transition has been formally accepted and signed off by DOST-STII and the Faculty Adviser. After the formal acceptance of the transition, all four team members will conclude their involvement with the project, with no ongoing obligations to DOST-STII for system maintenance or technical support beyond what is documented in the User Manual and deployment instructions.

Post-handover, full operational responsibility for the STARBOOKS Whiz Challenge passes entirely to DOST-STII. Mr. McGyver C. Basaya (STARBOOKS Lead Programmer) will serve as the system's primary technical owner, supported by the comprehensive documentation package delivered by the NEXUS team. DOST-STII management is expected to allocate appropriate staff time and budget for routine system maintenance, content updates, and event deployments, as documented in the system's operational assumptions in the SRS.

# Work Execution During Transition

Throughout the transition period, the remaining project work will continue to be executed by the team in accordance with the approved project schedule and WBS. The primary work activities during this period are:

- User Acceptance Testing (UAT): DOST-STII staff will conduct structured testing of all system functions against the test cases defined. The NEXUS team will triage and resolve any defects identified within the UAT period, prioritizing critical and high-severity issues.

- End-to-End Deployment Rehearsal: Arcielle Marie Gercan will lead the full deployment rehearsal on DOST-STII's actual kiosk hardware using the deployment package. This rehearsal validates the complete LAN setup, server configuration, database initialization, and client browser access.

- Documentation Finalization: Janice Maxene Salipande will complete and deliver all remaining documentation: the Software Requirements Specification, System Design Document, User Manual, Deployment and Setup Instructions, and archived project records. All documents will be uploaded to SharePoint and physically delivered to DOST-STII in the handover package.

- Knowledge Transfer Sessions: Technical and operational training sessions will be conducted by the NEXUS team for DOST-STII staff.

The NEXUS team retains full responsibility for all tasks and deliverables throughout the transition period. DOST-STII staff participating in UAT and knowledge transfer activities are acting as recipients and testers, not as owners of the work. Full operational responsibility transfers only upon formal acceptance at the end of the transition period.

# Subcontracts

The STARBOOKS Whiz Challenge project does not involve any subcontract agreements with third-party vendors or service providers. All development work was performed entirely by the four members of team NEXUS using free and open-source technologies (Flutter/Dart, Laravel, MongoDB, Laragon). No external subcontractors were engaged for any component of the system, and no third-party software maintenance contracts, licensing agreements, or service agreements are in place that would require transition actions.

The only external dependency relevant to the transition is the continued availability of the open-source frameworks and tools used in development (Flutter, Laravel, MongoDB, Laragon). These are all maintained by their respective open-source communities and carry no licensing costs or contract obligations that would affect DOST-STII's post-handover operations.

# Property Transition

## Government Furnished Equipment (GFE)

DOST-STII provided no Government Furnished Equipment (GFE) to NEXUS during the course of the project. All development work was performed on personally owned laptops and workstations belonging to the four team members, using DOST-STII's office space and internet access during scheduled meetings and sprint reviews only. No DOST-STII hardware, portable electronic devices, or identification credentials were issued to any of the team members and therefore no GFE return process is required.

Upon deployment, all system components including the server PC, client PCs, LAN router, and network equipment, will be provided and owned by DOST-STII, as specified in the SRS hardware section. NEXUS has no ownership claim over any DOST-STII hardware used during deployment or events.

## Incumbent Owned Equipment

All personally owned equipment used by NEXUS including development laptops, personal portable devices, and development environment configurations, will remain with the respective team members upon project closure. None of the team's personally owned equipment is required for the ongoing operation of the STARBOOKS Whiz Challenge system; the deployed system is fully self-contained on DOST-STII's kiosk hardware.

The complete deployment package including the application source code, database seed files, and all configuration files, will be delivered to DOST-STII as part of the handover package, ensuring that DOST-STII can independently redeploy or restore the system without any dependency on the team’s equipment.

## Intellectual Property

Per the project agreement between NEXUS and DOST-STII, all intellectual property produced as a direct result of the STARBOOKS Whiz Challenge project will be transferred to DOST-STII upon formal project acceptance. This includes:

- All application source code (Flutter/Dart frontend, Laravel backend, WebSocket server, MongoDB schema)

- All system documentation (SRS, System Design Document, User Manual, Deployment Instructions, Test Cases)

- All UML diagrams, data flow diagrams, entity relationship diagrams, and deployment diagrams

- All game assets created for the project

- All project management documentation (WBS, management plans, sprint records, meeting minutes)

DOST-STII will have full ownership rights to modify, extend, deploy, and maintain all transferred intellectual property. NEXUS retains no licensing rights or intellectual property claims over any project deliverable after formal acceptance. Any of the team members who continue to work on DOST-STII projects in future academic terms will do so under a new, separate project agreement.

## User Accounts and Passwords

The following table documents all system accounts and access credentials that must be transferred or disabled as part of the project handover. All NEXUS team member accounts on DOST-STII systems will be disabled or removed upon completion of the transition. DOST-STII will create new administrator accounts for their own staff using the admin management interface provided in the system.

| Account / System | Current Access Holder | Transition Action | New Owner |
| --- | --- | --- | --- |
| OpenProject Project Account | Kelly Dumbrique (Project Manager) | Export all project data to SharePoint; archive project in OpenProject; transfer account access to Faculty Adviser for academic record | SoCIT / Faculty Adviser |
| GitHub Repository | All NEXUS team members | Transfer repository ownership to DOST-STII GitHub account or deliver as a ZIP archive on physical media; revoke NEXUS team commit access after handover | DOST-STII (Mr. McGyver C. Basaya) |
| SharePoint Project Folder | All NEXUS team members | Deliver final document archive to DOST-STII; disable NEXUS team member access after confirmation of receipt | DOST-STII / Ms. Marievic V. Narquita |
| System Admin Account (STARBOOKS Whiz Challenge) | Arcielle Marie Gercan (created during development) | Reset admin credentials; create new admin accounts for designated DOST-STII staff during knowledge transfer; disable all NEXUS-created admin accounts | DOST-STII (Mr. McGyver C. Basaya) |
| MongoDB Database Admin Access | Arcielle Marie Gercan (Lead Developer) | Deliver database admin credentials; document all database admin procedures in the Deployment Instructions | DOST-STII (Mr. McGyver C. Basaya) |

# Knowledge Transfer

Knowledge transfer is the most critical component of this transition, as it determines DOST-STII's ability to independently operate, maintain, and update the STARBOOKS Whiz Challenge system after the NEXUS team disengages.

Session 1 — System Architecture and Deployment (Week 1) Led by Arcielle Marie Gercan (Lead Developer). This session covers the complete system architecture including the Docker-based deployment stack, LAN network configuration, MongoDB database setup, Laravel backend API structure, and WebSocket server operation. DOST-STII's technical lead (Mr. McGyver C. Basaya) is the primary audience. The session will include a hands-on deployment rehearsal on DOST kiosk hardware, walking through the full deployment procedure step by step against the written Deployment Instructions. Duration: half-day session.

Session 2 — Admin Dashboard Operations (Week 1) Led by Kelly Dumbrique (Project Manager) and Shandrae Lois Quianzon (Frontend Developer). This session covers all administrative dashboard functions: admin account management, player management, quiz content management, difficulty settings configuration, reward claim processing, leaderboard management, and analytics export. This session is targeted at DOST-STII administrative staff and the STARBOOKS Unit Lead. Duration: two-hour session with hands-on walkthrough.

Session 3 — Database Administration and Backup Procedures (Week 2) Led by Arcielle Marie Gercan (Lead Developer). This session covers MongoDB database administration including backup procedures, data restoration, basic query operations, and error recovery. This is a critical knowledge transfer given Risk R06 (MongoDB data loss) in the Risk Register. DOST-STII staff will practice the backup and restoration procedure independently before the session concludes. Duration: two-hour session.

Session 4 — Documentation Walkthrough and Q&A (Week 2) Led by Janice Maxene Salipande (Documentation Lead). This session walks through all delivered documentation — the SRS, System Design Document, User Manual, and Deployment Instructions — ensuring DOST-STII staff can locate relevant information independently. All outstanding documentation questions will be addressed. Any gaps identified during this session will be corrected before the final handover date. Duration: one-hour session.

Ongoing Support (Weeks 1–3) In addition to the formal sessions above, all NEXUS team members will be available via Viber throughout the transition period to respond to technical queries, assist with UAT defect resolution, and provide clarification on any documentation. Response to queries is expected within one working day during the transition period.

The Project Manager will convene a final transition readiness meeting with DOST-STII's technical lead and the Faculty Adviser no later than five days before the end of the transition period to confirm that all knowledge transfer activities have been completed adequately and that no further training is required before formal acceptance.

# Schedule

The following schedule outlines all major transition milestones across the transition period. Any changes to this schedule require agreement from both the Project Manager and the DOST-STII Project Sponsor.

(to be updated)

# Handover and Acceptance

Formal acceptance of the project handover will be determined by DOST-STII, represented by Ms. Marievic V. Narquita (STARBOOKS Unit Head). The acceptance process will proceed as follows:

Step 1 — UAT Sign-Off: DOST-STII operational staff confirm that all functional and non-functional requirements defined in the SRS have been validated through User Acceptance Testing, and that no critical or high-severity defects remain unresolved. The UAT completion record is signed by Mr. McGyver C. Basaya (STARBOOKS Lead Programmer) on behalf of DOST-STII.

Step 2 — Documentation Completeness Check: Janice Maxene Salipande presents the complete documentation package to the DOST-STII technical lead. DOST-STII confirms receipt of all required documents: SRS, System Design Document, User Manual, Deployment and Setup Instructions, Test Cases, and the archived project management records. Missing or incomplete items must be resolved before proceeding to Step 3.

Step 3 — Knowledge Transfer Confirmation: The NEXUS Project Manager and DOST-STII technical lead confirm that all four knowledge transfer sessions have been completed and that DOST-STII staff can independently perform all required operational tasks — deployment, admin operations, database backup, and basic troubleshooting.

Step 4 — Account and Credentials Transfer: Kelly Dumbrique and Arcielle Marie Gercan confirm that all system accounts have been transitioned, all NEXUS team access has been revoked, and new DOST-STII admin accounts are operational.

Step 5 — Faculty Adviser Academic Review: Sir Jose Eugenio Quesada confirms that all academic deliverables are complete and meet the course requirements. This step runs in parallel with Steps 1–4.

Step 6 — Formal Sign-Off: Upon confirmation that all preceding steps are complete, the following parties will sign the Project Turnover Record, which constitutes the formal acceptance of the transition:

- Ms. Marievic V. Narquita — DOST-STII Project Sponsor

- Mr. McGyver C. Basaya — DOST-STII Technical Lead

- Kelly Dumbrique — NEXUS Project Manager

- Sir Jose Eugenio Quesada — Project Adviser

It is only after all four signatures are obtained that the transition will be considered formally complete and the project officially closed. The signed Project Turnover Record will be archived on SharePoint and submitted as part of the academic project closure documentation.