Post Project Review

DOST STARBOOKS: Whiz Challenge

DOST Science and Technology Information Institute

Gen. Santos Ave., Upper Bicutan,

Taguig City, Metro Manila, 1631, Philippines

April 2026

Table of Contents

1.	Project Summary	3

2.	Project Team and Staffing	3

3.	Project Deliverables (Planned vs. Actual)	4

4.	Transition to Operations	5

5.	Project Costs	6

6.	Project Schedule	8

7.	Recommendations	9

# Project Summary

The STARBOOKS Whiz Challenge Project has been successfully completed and transitioned for deployment within the STARBOOKS platform under the Department of Science and Technology – Science and Technology Information Institute (DOST-STII). This project represents a significant initiative in enhancing digital learning experiences by integrating gamification into educational content accessible through STARBOOKS kiosks.

The primary objective of this project was to design and develop an interactive, gamified learning system that increases student engagement and improves knowledge retention. The system aimed to transform traditional access to educational resources into a more dynamic and competitive experience through features such as Memory Match, Puzzle Games, Whiz Challenge quizzes, and 1v1 Battle modes. Additionally, the project sought to support data-driven insights through leaderboard tracking and basic analytics, enabling educators and stakeholders to monitor participation and performance.

The purpose of the STARBOOKS Whiz Challenge Project was to maximize the value of existing STARBOOKS infrastructure by introducing an engaging, student-centered application without requiring additional financial investment. By leveraging open-source tools, student-led development, and existing kiosk systems, the project maintained a zero-cost implementation while delivering high-impact educational benefits.

The scope of the project included a structured, phased approach covering requirements gathering, system design, development, testing, and deployment. Key deliverables included user authentication, multiple game modules, leaderboard systems, and an administrative dashboard for monitoring usage and performance. The system was specifically designed to function in low-connectivity or offline environments, ensuring accessibility across various deployment locations.

Project success was defined by the system’s ability to meet functional and performance requirements, operate effectively within STARBOOKS kiosks, achieve high user engagement, and receive positive feedback from stakeholders. Furthermore, success included delivering a stable and user-friendly platform that could be deployed without significant changes to existing infrastructure.

# Project Team and Staffing

The STARBOOKS Whiz Challenge Project was carried out by a student-led development team in coordination with stakeholders from the Department of Science and Technology – Science and Technology Information Institute (DOST-STII). The team was composed of individuals fulfilling multiple roles across development, design, testing, and documentation, enabling efficient resource utilization while maintaining project quality. The table below provides details of the project team members:

| Name | Title | Project Role | Contact |
| --- | --- | --- | --- |
| A. Marievic V. Narquita | ISS Head of DOST-STII | Project Sponsor | a. mavie.narquita@stii.dost.gov.ph |
| B. Kelly Dumbrique | Project Manager | Project Manager / Frontend Developer | b. ksdumbrique2@student.apc.edu.ph |
| C. Arcielle Marie Gercan | Backend Developer | Technical Lead / Backend Development | c. acgercan@student.apc.edu.ph |
| D. Shandrae Lois Quianzon | UI/UX Designer | Frontend Developer / UI/UX Designer | d. saquianzon@student.apc.edu.ph |
| E. Janice Maxene Salipande | QA Lead | Frontend Developer / QA Lead / Documentation Lead | e. jdsalipande2@student.apc.edu.ph |
| F. DOST-STII Representatives | Management | Customer / Key Stakeholders | f. dost@dost.gov.ph |

The project team followed standard project management practices, including structured planning, iterative development, and continuous stakeholder engagement. Despite limited resources, the team effectively distributed responsibilities, with members taking on multiple roles to ensure all aspects of the project were addressed.

The team operated in a collaborative and flexible environment, allowing for efficient communication and quick decision-making. Regular coordination among team members and stakeholders ensured alignment with project goals and timely resolution of issues. The involvement of DOST-STII as both project sponsor and customer provided clear direction and ensured that the system met organizational and user requirements.

In terms of staffing strategy, the project adopted a lean approach by assigning essential roles only, avoiding over-allocation of resources. Each member was responsible for specific functional areas while also contributing to cross-functional tasks when necessary. This approach proved effective in maintaining efficiency while delivering all required project outputs within the defined constraints.

# Project Deliverables (Planned vs. Actual)

The STARBOOKS Whiz Challenge Project was completed successfully, with deliverables defined across key phases including system design, development, testing, and final deployment. The following tables present a comparison of planned versus actual deliverables.

System Design Phase

| Planned Deliverable | Actual Deliverable | Summary |
| --- | --- | --- |
| System architecture design, wireframes, and UI/UX prototypes | Completed system architecture design, wireframes, and UI/UX prototypes |  |

System Development Phase

| Planned Deliverable | Actual Deliverable | Summary |
| --- | --- | --- |
| Functional modules including login system, Memory Match, Puzzle Games, Whiz Challenge, and 1v1 Battle | Fully developed functional modules including login system, Memory Match, Puzzle Games, Whiz Challenge, and 1v1 Battle |  |
| Leaderboard system and analytics dashboard | Leaderboard system and basic analytics dashboard implemented |  |

Testing Phase

| Planned Deliverable | Actual Deliverable | Summary |
| --- | --- | --- |
| System testing documentation and validated test cases | Completed testing documentation and validated test cases with resolved major defects |  |

Final Project Deliverables

| Planned Deliverable | Actual Deliverable | Summary |
| --- | --- | --- |
| Fully functional STARBOOKS Whiz Challenge system integrated into kiosk environment | Fully functional system deployed and compatible with STARBOOKS kiosks |  |
| Administrative dashboard for monitoring user engagement and performance | Admin dashboard implemented with core tracking features |  |
| Documentation package (user guide, technical documentation, project reports) | Documentation package completed with minor enhancements recommended for future versions |  |
| Optimized offline-capable system for low-connectivity environments | System operates effectively in low-connectivity environments with optimized performance |  |

# Transition to Operations

Transitioning the system into an operational setting required close coordination between the project team, DOST-STII representatives, and participating schools. One of the key strengths of the transition process was the early and continuous involvement of stakeholders, particularly administrators and educators who would directly interact with the system. Their participation during testing and validation ensured that the system aligned with real-world educational use cases, minimizing deployment issues.

The transition process benefited significantly from the project’s low-cost and infrastructure-ready approach. Since the system was designed to run on existing STARBOOKS kiosks without requiring additional hardware or complex installations, deployment was efficient and did not disrupt ongoing operations. The use of open-source technologies and a web-based architecture further simplified system integration and reduced technical barriers. Key deliverables that supported a smooth transition included:

- Completed system documentation and user guides for administrators and educators

- Functional admin dashboard for managing content, users, and analytics

- Fully tested game modules (Memory Match, Puzzle, Whiz Challenge, 1v1 Battle)

- Analytics and leaderboard systems for monitoring engagement and performance

These deliverables ensured that operational users had both the tools and knowledge required to effectively utilize the system upon deployment.

Despite the overall success, some challenges were encountered during the transition. Connectivity limitations in certain deployment environments required additional optimization to ensure offline or low-bandwidth functionality. Additionally, minor user interface adjustments were necessary based on feedback from initial users to improve usability and accessibility for students. Several best practices emerged from this transition:

- Early stakeholder involvement greatly improved system relevance and acceptance

- Iterative testing with real users ensured smoother deployment and reduced post-launch issues

- Leveraging existing infrastructure minimized costs and implementation complexity

- Clear documentation and training materials enabled faster adoption by end users

For future projects, it is recommended to involve operational users even earlier during the prototype development stage and to conduct pilot deployments in multiple environments to better anticipate infrastructure-related challenges.

# Project Costs

Unlike traditional projects with significant financial allocations, this project focused on maximizing available resources, including student expertise, existing STARBOOKS kiosks, and freely available development tools. This approach eliminated the need for expenditures related to software licensing, hardware procurement, and external services. The table below summarizes the comparison of planned and actual costs by project phase:

| Project Phase | Budgeted Cost | Actual Cost | Comments |
| --- | --- | --- | --- |
| Requirements & Planning | ₱0.00 | ₱0.00 | Conducted by project team as part of academic initiative |
| System Design | ₱0.00 | ₱0.00 | Utilized open-source design tools and internal expertise |
| Development (Phases 1 & 2) | ₱0.00 | ₱0.00 | Student developers implemented all features without cost |
| Testing & Quality Assurance | ₱0.00 | ₱0.00 | Internal testing and user validation conducted at no cost |
| Deployment & Implementation | ₱0.00 | ₱0.00 | Deployed using existing STARBOOKS kiosks |
| Training & Documentation | ₱0.00 | ₱0.00 | Materials created and distributed digitally |

The project successfully achieved all planned deliverables without incurring financial expenses. This is primarily attributed to:

- Student-led development model, eliminating labor costs

- Use of open-source tools, removing licensing fees

- Existing infrastructure utilization, avoiding hardware and deployment costs

- Efficient planning and scope control, preventing cost overruns

There were no instances of scope creep, budget overruns, or unexpected expenses throughout the project. However, it is important to note that while no financial costs were incurred, the project required significant time investment, technical effort, and coordination, which can be considered as non-monetary resources.

From a project management perspective, this initiative demonstrates that high-impact digital solutions can be delivered with minimal financial resources, provided that planning, stakeholder collaboration, and resource utilization are effectively managed.

For future implementations or scaling of the project (e.g., nationwide deployment), potential costs may arise in areas such as infrastructure upgrades, maintenance, and training. These should be considered in subsequent project phases or expansions.

# Project Schedule

The STARBOOKS Whiz Challenge Project followed a planned multi-phase schedule beginning in April 2025 and concluding in October 2026. The timeline was structured to support progressive development of player-side features, administrative tools, testing activities, deployment preparation, and final turnover to the Department of Science and Technology – Science and Technology Information Institute (DOST-STII).

The project schedule was intentionally divided into phases to allow early delivery of core player-side modules while administrative components and final deployment activities continued in later stages. This phased approach enabled testing and feedback collection before full system turnover.

At the start of the project, the team identified potential schedule risks such as limited manpower, academic workload conflicts, and the complexity of integrating multiple game modules into kiosk-ready environments. Through proper planning, milestone tracking, and continuous communication, the project maintained steady progress throughout its lifecycle. The table below compares the planned schedule dates with the actual completion status of each project phase:

| Project Phase | Scheduled Completion | Actual Completion | Comments |
| --- | --- | --- | --- |
| Requirements Gathering & Planning | August 31, 2025 | August 31, 2025 | Completed on time |
| Development Phase 1 (Player-side) | October 31, 2025 | November 5, 2025 | Minor extension for gameplay polishing |
| Development Phase 2 (Admin-side) | February 28, 2026 | March 10, 2026 | Slight extension for dashboard refinement |
| Soft Deployment, Testing, and Player-Side Optimization | June 2026 | May 2026 | Completed on time |
| Final Deployment, System Completion, and Turnover | October 2026 |  |  |

# Recommendations

The STARBOOKS Whiz Challenge Project was a well-planned and successfully executed initiative which delivered an engaging educational platform ahead of schedule and at zero financial cost. However, several recommendations and lessons learned were identified which can further strengthen future projects.

Recommendation #1: Engage End Users Earlier During Initial Planning and Prototyping

While stakeholder participation was present throughout the project, future initiatives would benefit from involving students, teachers, and administrators even earlier during the concept and prototype stages. Early user feedback can improve feature prioritization, usability, accessibility, and alignment with actual learning needs before development begins. This would allow project teams to validate assumptions sooner and reduce the need for later design revisions.

Recommendation #2: Conduct Multi-Environment Pilot Testing Before Full Deployment

The project successfully completed soft deployment and kiosk testing; however, future implementations should expand pilot testing across multiple schools or locations with varying technical environments. Differences in hardware specifications, network availability, and user behavior may reveal issues not visible in controlled testing environments. Testing in diverse real-world environments can improve readiness for broader rollout and reduce post-deployment adjustments.

Recommendation #3: Maintain a Central Repository of Project Documents and Templates

The project generated valuable materials such as schedules, requirements documents, technical references, user manuals, testing results, and management plans. Future teams should maintain these in a centralized repository for easy access and reuse. Studying past project documentation can help future teams more accurately estimate schedules, identify risks, reuse templates, and avoid repeating common mistakes

Recommendation #4: Continue Using Incremental Development and Parallel Testing

One major success factor of the project was the ability to develop modules in phases while simultaneously conducting testing and refinement. This reduced delays and enabled the project to finish ahead of schedule. Future projects should continue using phased development models with overlapping testing cycles to improve speed, quality, and responsiveness.

Recommendation #5: Plan Around Academic and Resource Constraints

Because the project team consisted of student developers, academic schedules, examinations, and limited availability created potential risks. Future academic-based projects should formally include contingency buffers for peak academic periods and assign backup responsibilities where possible. This will help maintain momentum even during periods of reduced team availability.

Recommendation #6: Expand Analytics and Reporting Features for Long-Term Use

The STARBOOKS Whiz Challenge system includes leaderboards and analytics features. Future versions should further enhance reporting capabilities such as learning progress trends, participation rates, content difficulty analysis, and school performance dashboards. These insights can support data-driven decision-making for educators and DOST-STII management.

Sponsor Acceptance

Approved by the Project Sponsor:

Date: May 22, 2026

Marievic V. Narquita

# Information Services Section (ISS) Head of DOST-STII